**NGMC Tower, CEP, and ED Schedule Information**

1. **Tower Risers rough in timeline**
   1. Schedule shows a 20-day duration, which would be a total of 41 electricians. We believe this will require 80 days with average of 10 men, 6,863 hrs.
2. **Tower 5th and 6th floors**…Schedule shows a 70-day duration for MEP OH Rough-in, average of 29 electricians.
   1. Tower 5th floor Overhead Rough…5,750 hrs.
   2. Tower 6th floor Overhead Rough…10,963 hrs.
   3. 5th and 6th floor In-wall - 60 Days, average 3 electricians…1,217 hrs.
   4. 5th and 6th floor Wire - 70 Days, average 4 electricians…2,341 hrs.
   5. 5th and 6th floor Trim 45 Days, average 5 electricians…1,917 hrs.
3. **CEP Rough-In Timeline**…Schedule interpreted as approximately 170 days for electrical, average 8 electricians…11,251 hrs.
4. **ED Basement (Pharmacy / Lab)** – Overhead rough, in-wall rough, wire pulling timelines
   1. Overhead - 90 Days, average 25 electricians, 20,547 hrs.
   2. In-wall - 30 Days, average 9 electricians, 2,283 hrs.
   3. Wire - 30 Days, average 25 electricians, 6,136 hrs.
   4. Trim - 20 Days, average 9 electricians, 1,509 hrs.
5. **ED 1st Floor (ED)** – Overhead rough, in-wall rough, wire pulling timelines
   1. Overhead - 45 Days, average 29 electricians, 10,712 hrs.
   2. In-wall - 30 Days, average 5 electricians, 1,190 hrs.
   3. Wire - 30 Days, average 15 electricians, 3,572 hrs.
   4. Trim - 20 Days, average 18 electricians, 2,819 hrs.
6. **ED 2nd Floor (Surgery / Prep Recovery)** – Overhead rough, in-wall rough, wire pulling timelines
   1. Overhead - 60 Days, average 19 electricians, 9,314 hrs.
   2. In-wall - 40 Days, average 4 electricians, 1,035 hrs.
   3. Wire - 30 Days, average 11 electricians, 2,728 hrs.
   4. Trim - 25 Days, average 10 electricians, 1,972 hrs.
7. **ED 3rd Floor (Penthouse)** – Overhead rough, in-wall rough, wire pulling timelines…Schedule shows 60 Days, average 4 electricians.
   1. Overhead - 1,241 hrs.
   2. In-wall - 62 hrs.
   3. Wire - 394 hrs.
   4. Trim - 279 hrs.

Total Labor for Tower and CEP Only…**40,302 hrs.**

Total Labor for Tower, CEP, and ED…**106,095 hrs.** (ED Total Labor…65,793 hrs.)